## ChangeSummary
Differences from February 2020 Calendar and March 2020 Calendar are as follows:
Released
ACE Initiative - Field Payroll - GEAC decommission - released as planned 02/28/2020
Agent Portal February released as planned 02/28/2020 (Field Payroll - Part 2; NLFC incentive tracking enhancements)
Added
Agent Portal March release includes Premium Increase Program (PIP) Phase 2 - planned 03/31/2020 (postponed from February release)
Agent Portal April release includes Client Intelligence, New Business Case Trackers, Transfer/Exchange/Rollover Report – Part 2 - planned 04/30/2020
2020 SPDA Enhancements release planned 06/29/2020
Changed
Premium Increase Program (PIP) Simplification - release changed from 03/20/2020 to 03/30/2020
TotalSecure Inforce Illustrations - release changed from 03/28/2020 to 04/06/2020

## 2020 March
2020 - NLG Home Office Landing Calendar (as of March 2020)
Project IMPACT Details - L/M/S
2020 Start Date | Impact Date | Buying Cust | Selling Cust | Sales Desk | Client Partner | Help Desk | Contact Ctr | Operations | FMG | Project | SEF Program | Business Owner | SBT Owner
2020-01-02 | 2020-03-30 | M | M |  | M |  |  |  |  | Premium Increase Program (PIP) Simplification | Distribution | MaryAnn Ellis | Lynn Lovell | 88
2020-01-02 | 2020-03-31 | S | S | [5 empty] | M | Principles Based Reserves | Enterprise | Susan Yuan | Sandeep Viswanatha | 89
2020-01-02 | 2020-03-31 | S | M |  | S | S | S | M |  | Agent Portal - March 2020 Release | Customer | Ryan Matherly | Ravi Konkimalla | 89
2020-01-02 | 2020-04-06 | S | M | M | S | S | S | S |  | TotalSecure Inforce Illustrations | Growth | Erika George | Elizabeth Waring | 94
2020-01-02 | 2020-04-30 | S | M |  | S | S | S | M |  | Agent Portal - April 2020 Release | Customer | Ryan Matherly | Ravi Konkimalla | 118
2020-01-02 | 2020-06-29 | L | L | L | L | S | M | L | M | 2020 SPDA Enhancements | Growth | Dan Adams | Anna Travers | 177

## 2020 March Desc
Project Details (as of March 2020)
Project Name | Business Owner | Tracking No. | Description | Actual Start Date
Premium Increase Program (PIP) Simplification | MaryAnn Ellis | 13416 | This project is to create an improved PIP that incentivizes agents to meet with clients, conduct policy reviews, and increase flow contributions to help clients reach their goals and maximize new flow premium for NLG. Phase 2 changes include allowing multiple PIP increases per year, providing a way for agents to self report increases before 2 consecutive payments are received, resetting the High Water Mark to the actual premium received in the last 12 months, and the ability to have PIP applied only on a certain number of payments. | 2019-01-01
Principles Based Reserves | Susan Yuan | 13005 | The NAIC has adopted new statutory reserve standards effective for life insurance policies issued after January 1, 2017, with an optional 3-year in phase - in. The objective of the project is to be in a position to comply with the new standards by 2020. We are currently updating our valuation processes and will be ready to report our statutory reserves on a PBR basis starting 1Q20 for policies issued after 1/1/2020. | 2017-03-01
Agent Portal - March 2020 Release | Ryan Matherly | Varies | March release includes: Premium Increase Program (PIP) Phase 2 | 2020-03-01
TotalSecure Inforce Illustrations | Erika George | 13494 | This launch will deliver ITS-enabled Illustrations for in-force policies. This is regulatory functionality require done year after product sales launch. Illustrations will be run manually on-demand until this launches to Production. | 2019-10-28
Agent Portal - April 2020 Release | Ryan Matherly | Varies | April release: Client Intelligence is a new dashboard on the agent portal that helps agents uncover sales and servicing opportunities by surfacing all client interactions that happen in the contact centers and via the client portal and mobile app, as well as information about key policy and client life events. There is an individual and an upline view. Users can subscribe to daily or weekly digests via email or text. The dashboard contains two months of data and updates hourly, making it a timely way to keep on top of one’s book of business. It has been in pilot since October with 7 agencies and has received rave reviews. Drawing inspiration from FedEx and Amazon package trackers (and the infamous Dominos “Pizza Tracker”), our New Business Case Trackers for both Life and Annuity policies under $250K will help agents better where their cases are within the New Business process. This is a first effort. The goal is to get feedback from users and improve the trackers over time and as an input to our longer-term strategy. One of our key enhancements will be to help agents understand which requirements they need to address and which NLG is taking care of. Last fall we launched a new Transfer/Exchange/Rollover report that helps agents better manage incoming transfers. We are enhancing the initial report with better policy and client search as well as adding Total Number of Transfers, Total Amount Expected, and Anticipated Annual Premium. | 2020-04-01
2020 SPDA Enhancements | Dan Adams | 13521 | We are replacing the existing SPDA products with an enhanced portfolio to improve profitability and competitiveness.&#160; Key enhancements include: modernizing indices and crediting strategies such as introduction of a buy up charge strategy, include an enhanced death benefit to simplify the choice between FIT and Marquee/Preferred, Restore CA commissions by including MVA, enhance GLIR, add bonus recapture, and Change minimum premium from $10k to $100k​ | 2020-01-13